## active projects
Active Projects
Enhancements
Name | Subitems | Person | Status | Date assigned | Go Live Date | Item ID (auto generated)
WhatsApp | [5 empty] | 18311576141
Turnkey LOS
Name | Subitems | Person | Status | Date assigned | Go Live Date | Item ID (auto generated)
Turnkey - Phase 1 (Decision Engine, Borrower Portal, and Pricing Engine) | Provide List of Application Fields (Regular & Anywhere),Provide Decision Engine Logic,Provide Pricing Engine Spreadsheet,Provide Fee Rules,Provide File Contacts,Provide Role Status Matrix,Provide Loan Access Hierarchy,Provide Loan Status, Roles, and Loan Flow,Provide Role Access To Status,Choose Document Generator Vendor,Choose Payment Provider Vendor,Review BRD and make Changes if Necessary,Test Decision Engine (Phase 1),Integrating Turnkey with ENC (discovery phase),Decision Engine Field Development,Loan Application Page,Send Document Templates to Turnkey,Work with them to integrate TK to ENC | Oscar Gatica | Ongoing Build |  | 2025-04-01 | 9547006379
Subitems | Name | Owner | Status | Date | Go Live Date | Item ID (auto generated)
| Provide List of Application Fields (Regular & Anywhere) | Oscar Gatica | Done |  |  | 9547149448
| Provide Decision Engine Logic | Oscar Gatica | Done |  |  | 9547152065
| Provide Pricing Engine Spreadsheet | Oscar Gatica | Done |  |  | 9547153186
| Provide Fee Rules | Oscar Gatica | Done |  |  | 9547237837
| Provide File Contacts | Oscar Gatica | Done |  |  | 9547239534
| Provide Role Status Matrix | Oscar Gatica | Done |  |  | 9547241287
| Provide Loan Access Hierarchy | Oscar Gatica | Done |  |  | 9547242347
| Provide Loan Status, Roles, and Loan Flow | Oscar Gatica | Done |  |  | 9547244453
| Provide Role Access To Status | Oscar Gatica | Done |  |  | 9547245308
| Choose Document Generator Vendor | Oscar Gatica | Done |  |  | 9547249046
| Choose Payment Provider Vendor | Oscar Gatica | Working on it |  |  | 9547251056
| Review BRD and make Changes if Necessary | Oscar Gatica | Done |  |  | 9710285887
| Test Decision Engine (Phase 1) | Oscar Gatica | Pending Vendor |  |  | 9923247246
| Integrating Turnkey with ENC (discovery phase) | Oscar Gatica | Pending Vendor |  |  | 10043090817
| Decision Engine Field Development | Oscar Gatica | Pending Vendor |  |  | 10063136970
| Loan Application Page | Oscar Gatica | Pending Vendor |  |  | 10063139478
| Send Document Templates to Turnkey | Oscar Gatica | Done |  |  | 18077906735
| Work with them to integrate TK to ENC | Oscar Gatica | Working on it |  |  | 18077908926
2025-04-01
IT Projects - December
Name | Subitems | Person | Status | Date assigned | Go Live Date | Item ID (auto generated)
Added an Encompass custom field, to fix an issue with how plural words were printing in the promissory note custom form "cx.es" |  | Oscar Gatica | Done |  |  | 9710456509
Negotiated the KnowBe4 pricing to remain the same, instead of it increasing to $200+ |  | Oscar Gatica | Done |  |  | 9710457212
Completed Word Doc Update for Alex |  | Oscar Gatica | Done |  |  | 9710457678
Participated in project request meetings with each department |  | Oscar Gatica | Done |  |  | 9710459254
IT Projects - January
Name | Subitems | Person | Status | Date assigned | Go Live Date | Item ID (auto generated)
Created a fee template for "The Village" in Encompass |  | Oscar Gatica | Done |  |  | 9710446874
Synced Leadsource from Contact to Loan object in SF |  | Oscar Gatica | Done |  |  | 9710448034
Created new Encompass disclosure scenario |  | Oscar Gatica | Done |  |  | 9710448907
Helped Moxi employees with the office365 migration |  | Oscar Gatica | Done |  |  | 9710449297
Reconnected the SF office365 connection |  | Oscar Gatica | Done |  |  | 9710450107
Updated the office365 Hello@moxi.global inbox plugin inside of Encompass |  | Oscar Gatica | Done |  |  | 9710450579
Signed with Dialpad and extended 1 month of zoom (plans to cancel zoom) |  | Oscar Gatica | Done |  |  | 9710451072
Began decision engine scoping calls |  | Oscar Gatica | Done |  |  | 9710452047
IT Projects - February
Name | Subitems | Person | Status | Date assigned | Go Live Date | Item ID (auto generated)
Created Development to Company hierarchy in Salesforce. |  | Oscar Gatica | Done |  |  | 9710435477
Began project build with Dialpad |  | Oscar Gatica | Done |  |  | 9710435667
Fixed issue with an ENC calculation fields |  | Oscar Gatica | Done |  |  | 9710436935
Completed 2 projects for Amy |  | Oscar Gatica | Done |  |  | 9710439298
Began and completed sharefile migration | Migrated all storage items from our palisades sharefile, to our MoXi sharefile. | Oscar Gatica | Done |  |  | 9710439695
Subitems | Name | Owner | Status | Date | Go Live Date | Item ID (auto generated)
| Migrated all storage items from our palisades sharefile, to our MoXi sharefile. | Oscar Gatica | Done |  |  | 9710442210
IT Projects - March
Name | Subitems | Person | Status | Date assigned | Go Live Date | Item ID (auto generated)
Completed Encompass enhancement projects for Amy |  | Oscar Gatica | Done |  |  | 9710391773
Bought and installed the batch update tool, to ease the amount of manual work fpr Melissa's team and tech |  | Oscar Gatica | Done |  |  | 9710393113
Set up the SF+AC+Zap integration to capture better marketing details. | Installed ActiveCampaign package in salesforce,Configured widget in the contact object,Synced numerous fields from SF over to ActiveCampaign | Oscar Gatica | Done |  |  | 9710393582
Subitems | Name | Owner | Status | Date | Go Live Date | Item ID (auto generated)
| Installed ActiveCampaign package in salesforce |  |  |  |  | 9710394734
| Configured widget in the contact object |  |  |  |  | 9710396238
| Synced numerous fields from SF over to ActiveCampaign |  |  |  |  | 9710397548
Met with 10 decision engine companies to find our best fit |  | Oscar Gatica | Done |  |  | 9710398713
Fixed SF Tree of Knowledge (After O365 migration) |  | Oscar Gatica | Done |  |  | 9710401977
Configured and launched CodeTwo | Configured signature templates internally and externally for all employees | Oscar Gatica | Done |  |  | 9710402785
Subitems | Name | Owner | Status | Date | Go Live Date | Item ID (auto generated)
| Configured signature templates internally and externally for all employees |  |  |  |  | 9710406814
Configured and Launched Bookings | Set up all MA, Client Concierge, and miscellaneous booking pages | Oscar Gatica | Done |  |  | 9710403443
Subitems | Name | Owner | Status | Date | Go Live Date | Item ID (auto generated)
| Set up all MA, Client Concierge, and miscellaneous booking pages |  |  |  |  | 9710411649
Configured and Launched Dialpad | Registered MoXI to be in compliance with SMS guidelines,Ported over all of our US and MX numbers,Configured departments,Configured admin settings,Conducted training to our users | Oscar Gatica | Done |  |  | 9710413714
Subitems | Name | Owner | Status | Date | Go Live Date | Item ID (auto generated)
| Registered MoXI to be in compliance with SMS guidelines | Oscar Gatica | Done |  |  | 9710423171
| Ported over all of our US and MX numbers | Oscar Gatica | Done |  |  | 9710415931
| Configured departments | Oscar Gatica | Done |  |  | 9710416162
| Configured admin settings | Oscar Gatica | Done |  |  | 9710416837
| Conducted training to our users | Oscar Gatica | Done |  |  | 9710418233
Migrated our users away from Zoom and onto Teams |  | Oscar Gatica | Done |  |  | 9710414886
Onboarded 2 new hires (alivia and guillermo) |  | Oscar Gatica | Done |  |  | 9710424027
Created new flows in SF, to trigger timed emails for borrowers |  | Oscar Gatica | Done |  |  | 9710424881
IT Projects - April
Name | Subitems | Person | Status | Date assigned | Go Live Date | Item ID (auto generated)
Configured Zapier to send MA calendar events from outlook into Salesforce for better tracking |  | Oscar Gatica | Done |  |  | 9710350230
Set up MoXi Anywhere tech configuration & flows | Consumer Connect Site configuration,Consumer Connect Workflow,Encompass Configuration,Encompass Disclosure Configuration,ActiveCampaign lead nurture emails,ActiveCampaign Timed Emails,Zapier lead collecting flow,Outlook Mailbox | Oscar Gatica | Done |  |  | 9710356617
Subitems | Name | Owner | Status | Date | Go Live Date | Item ID (auto generated)
| Consumer Connect Site configuration | Oscar Gatica | Done |  |  | 9710357346
| Consumer Connect Workflow | Oscar Gatica | Done |  |  | 9710357964
| Encompass Configuration | Oscar Gatica | Done |  |  | 9710358541
| Encompass Disclosure Configuration | Oscar Gatica | Done |  |  | 9710360759
| ActiveCampaign lead nurture emails | Oscar Gatica | Done |  |  | 9710362542
| ActiveCampaign Timed Emails | Oscar Gatica | Done |  |  | 9710363011
| Zapier lead collecting flow | Oscar Gatica | Done |  |  | 9710365063
| Outlook Mailbox | Oscar Gatica | Done |  |  | 9710366294
Coded MoXi Anywhere loans to have a unique pre-fix |  | Oscar Gatica | Done |  |  | 9710429925
Taught myself how to use the Windows PowerShell Command System to run scripts on our Office365 Tenant |  | Oscar Gatica | Done |  |  | 9710369017
Trained Chris how to use the ENC batch update tool |  | Oscar Gatica | Done |  |  | 9710372059
Created a Marketing Touchpoint custom object in SF to capture each time a lead opted in via marketing. | Created a SF flow to notify the contact owner MA of re-opt,Created a SF flow to notify the contact that we received their re-opt | Oscar Gatica | Done |  |  | 9710372583
Subitems | Name | Owner | Status | Date | Go Live Date | Item ID (auto generated)
| Created a SF flow to notify the contact owner MA of re-opt | Oscar Gatica | Done |  |  | 9710375039
| Created a SF flow to notify the contact that we received their re-opt | Oscar Gatica | Done |  |  | 9710377234
Updated every lead capture Zap (38) to check if the lead already exists as a contact, to reduce our duplicate issue |  | Oscar Gatica | Done |  |  | 9710378058
Onboarded 1 new hire (mike) |  | Oscar Gatica | Done |  |  | 9710381464
IT Projects - May
Name | Subitems | Person | Status | Date assigned | Go Live Date | Item ID (auto generated)
Built a secondary BDO field on the SF buisiness contact level |  | Oscar Gatica | Done |  |  | 9710296152
Updated the Ellie Mae lead source flow from ENC to SF. |  | Oscar Gatica | Done |  |  | 9710298139
Build the marketing touchpoint further, to start using it for email notifications to client re-opts |  | Oscar Gatica | Done |  |  | 9710298787
Configured Voicemail Zap to have quiet hours |  | Oscar Gatica | Done |  |  | 9710339259
Began Scoping Turnkey Partner Integrations for a Document generator and Payment provider |  | Oscar Gatica | Done |  |  | 9710343796
IT Projects - June
Name | Subitems | Person | Status | Date assigned | Go Live Date | Item ID (auto generated)
Restrict Contact Owner, BDO, BDO2 fields in Salesforce & Create Approval Process |  | Oscar Gatica | Done |  | 2025-06-17 | 9547006398
Setup Timed Emails For Retail | Sync the following fields from ENC to SF - Subj. Prop, Application Date, Docs Missing, Fee Missing,Created a Flow in Saleforce that pushes the Subj. prop address from the Loan object to it's related contact object, upon creation/update,Sync Subj. Prop Address and Application Date from Salesforce to ActiveCampaign,Create 3 separate automations in ActiveCampaign to fire depending on the loan scenario,Build and configure a total of 21 Email campaigns in ActiveCampaign to assign to it's corresponding Automation | Oscar Gatica | Done |  | 2025-06-25 | 9547006416
Subitems | Name | Owner | Status | Date | Go Live Date | Item ID (auto generated)
| Sync the following fields from ENC to SF - Subj. Prop, Application Date, Docs Missing, Fee Missing | Oscar Gatica | Done |  |  | 9547452147
| Created a Flow in Saleforce that pushes the Subj. prop address from the Loan object to it's related contact object, upon creation/update | Oscar Gatica | Done |  |  | 9547464042
| Sync Subj. Prop Address and Application Date from Salesforce to ActiveCampaign | Oscar Gatica | Done |  |  | 9547467653
| Create 3 separate automations in ActiveCampaign to fire depending on the loan scenario | Oscar Gatica | Done |  |  | 9547479015
| Build and configure a total of 21 Email campaigns in ActiveCampaign to assign to it's corresponding Automation | Oscar Gatica | Done |  |  | 9547482637
Renew Adobe License |  | Oscar Gatica | Done |  | 2025-06-27 | 9547502351
Offboarded MA - Ariel G |  | Oscar Gatica | Done |  |  | 9547515403
Onboarded new MA - Yaneth M |  | Oscar Gatica | Done |  |  | 9547516484
2025-06-17 to 2025-06-27
IT Projects - July
Name | Subitems | Person | Status | Date assigned | Go Live Date | Item ID (auto generated)
Add SMS automation to Re-Opts in Salesforce |  | Oscar Gatica | Enhancement Request |  |  | 9564860015
B2B Drip Campaign (Zap ¦ ActiveCampaign ¦ Salesforce) | Re-Configured the 3 Developer, Broker, Realtor Zaps to create a Contact, Company & Development Object.,Created 2 Automations in ActiveCampaign (Developer & Broker/Realtors) and configured 24 Email Campaigns.,Batch updated over 5000+ contacts, with a new Campaign field, so that they are automatically entered into their respective drip campaign in AC | Oscar Gatica | Done |  | 2025-07-01 | 9637103869
Subitems | Name | Owner | Status | Date | Go Live Date | Item ID (auto generated)
| Re-Configured the 3 Developer, Broker, Realtor Zaps to create a Contact, Company & Development Object. | Oscar Gatica | Done |  |  | 9637113677
| Created 2 Automations in ActiveCampaign (Developer & Broker/Realtors) and configured 24 Email Campaigns. | Oscar Gatica | Done |  |  | 9637152493
| Batch updated over 5000+ contacts, with a new Campaign field, so that they are automatically entered into their respective drip campaign in AC | Oscar Gatica | Done |  |  | 9637179709
Twilio/Salesforce SMS configuration | Registered our new Twilio numbers to the SMS regulation committee,Configured thew new numbers in Salesforce through the Integration settings, and assigned them to the correct sales staff member.,Configured Salesforce Flows to send out SMS texts, to new clients with Quiet Hours. (More Details In Comments) | Oscar Gatica | Done |  |  | 9637201986
Subitems | Name | Owner | Status | Date | Go Live Date | Item ID (auto generated)
| Registered our new Twilio numbers to the SMS regulation committee | Oscar Gatica | Done |  |  | 9637276961
| Configured thew new numbers in Salesforce through the Integration settings, and assigned them to the correct sales staff member. | Oscar Gatica | Done |  |  | 9637282743
| Configured Salesforce Flows to send out SMS texts, to new clients with Quiet Hours. (More Details In Comments) | Oscar Gatica | Done |  |  | 9637307384
Kajabi Double Opt In Verification | Set up email configuration in Kajabi,Created an automation to send email verifications to form submitters, then replicated it for 7 other forms.,Reconfigured Zap to catch all verified customers in Kajabi, pull them in and flow them over to Salesforce. | Oscar Gatica | Done | 2025-07-11 | 2025-07-15 | 9637335297
Subitems | Name | Owner | Status | Date | Go Live Date | Item ID (auto generated)
| Set up email configuration in Kajabi | Oscar Gatica | Done |  |  | 9637626857
| Created an automation to send email verifications to form submitters, then replicated it for 7 other forms. | Oscar Gatica | Done |  |  | 9637629908
| Reconfigured Zap to catch all verified customers in Kajabi, pull them in and flow them over to Salesforce. | Oscar Gatica | Done |  |  | 9637642605
Do Not Contact ActiveCampaign Flow | Synced the "Do Not Contact" field from Salesforce to ActiveCampaign, and updated all of our automations to recognize if a contact contains that field and opt them out accordingly. | Oscar Gatica | Done | 2025-07-17 | 2025-07-18 | 9637659669
Subitems | Name | Owner | Status | Date | Go Live Date | Item ID (auto generated)
| Synced the "Do Not Contact" field from Salesforce to ActiveCampaign, and updated all of our automations to recognize if a contact contains that field and opt them out accordingly. | Oscar Gatica | Done |  |  | 9637669408
Salesforce Milestone Cleanup | Re-sync the Milestones in the Jungo Sync Tool,Update the Path status in the Loan object,Created a flow to keep Milestone, status, path status | Oscar Gatica | Done |  | 2025-07-22 | 9639726544
Subitems | Name | Owner | Status | Date | Go Live Date | Item ID (auto generated)
| Re-sync the Milestones in the Jungo Sync Tool | Oscar Gatica | Done |  |  | 9665166734
| Update the Path status in the Loan object | Oscar Gatica | Done |  |  | 9665169355
| Created a flow to keep Milestone, status, path status | Oscar Gatica | Done |  |  | 9665179777
ActiveCampaign 52 week Drip Email Campaign | Build out the email automation flow | Oscar Gatica | Done | 2025-07-25 | 2025-08-15 | 9676179136
Subitems | Name | Owner | Status | Date | Go Live Date | Item ID (auto generated)
| Build out the email automation flow | Oscar Gatica | Working on it |  |  | 9676181135
Configured new encompass transcript ordering service | Trained Linda, Carlos and Amy | Oscar Gatica | Done |  | 2025-07-28 | 9676437374
Subitems | Name | Owner | Status | Date | Go Live Date | Item ID (auto generated)
| Trained Linda, Carlos and Amy | Oscar Gatica | Working on it |  |  | 9676437817
English to Spanish translation solution for Team Meetings. | Teams Premium License Worked | Oscar Gatica | Done | 2025-07-25 | 2025-07-29 | 9690146559
Subitems | Name | Owner | Status | Date | Go Live Date | Item ID (auto generated)
| Teams Premium License Worked | Oscar Gatica | Done |  |  | 9699435747
Assisted Chris by syncing the salesforce referral fields between Contact, Company, and Loan object. |  | Oscar Gatica | Done | 2025-07-29 | 2025-07-29 | 9699445410
|  |  |  | 2025-07-11 to 2025-07-29 | 2025-07-01 to 2025-08-15
IT Projects - August
Name | Subitems | Person | Status | Date assigned | Go Live Date | Item ID (auto generated)
Onboarded New Hires - Victoria & Mary |  | Oscar Gatica | Done | 2025-07-28 | 2025-08-11 | 9709033969
MA Landing Page Lead Source Enhancement | Created a custom field in ENC [CX.LandingPage],Pre-defined the field for every MA in our Mortgage Application. Then Added it to the App Custom Code.,Synced the ENC field to Salesforce,Created a flow in SF that detects the LandingPage field, and set it to update the contact leadsource | Oscar Gatica | Done | 2025-08-19 | 2025-08-25 | 9739322135
Subitems | Name | Owner | Status | Date | Go Live Date | Item ID (auto generated)
| Created a custom field in ENC [CX.LandingPage] | Oscar Gatica | Done |  |  | 9896731295
| Pre-defined the field for every MA in our Mortgage Application. Then Added it to the App Custom Code. | Oscar Gatica | Done |  |  | 9896733186
| Synced the ENC field to Salesforce | Oscar Gatica | Done |  |  | 9896733758
| Created a flow in SF that detects the LandingPage field, and set it to update the contact leadsource | Oscar Gatica | Done |  |  | 9896735674
Enhance the Retail Timed email automations and add more configuration | Retail Timed Emails - App Fee Not Paid + Docs Missing (Property identified) - Finished,MoXi Retail Timed Emails - App Fee Not Paid + Docs Uploaded (Property identified),MoXi Retail Timed Emails - App Fee Not Paid + Docs Uploaded (Property identified),MoXi Retail Timed Emails - App Fee Not Paid + Docs Missing (TBD),MoXi Retail Timed Emails - App Fee Not Paid + Docs Uploaded (TBD),MoXi Retail Timed Emails - App Fee Paid + Docs Missing (TBD),Synced Contact owner, Phone, Email from SF to AC,Configured 28 emails | Oscar Gatica | Done | 2025-08-19 | 2025-08-26 | 9761237487
Subitems | Name | Owner | Status | Date | Go Live Date | Item ID (auto generated)
| Retail Timed Emails - App Fee Not Paid + Docs Missing (Property identified) - Finished | Oscar Gatica |  |  |  | 9791596045
| MoXi Retail Timed Emails - App Fee Not Paid + Docs Uploaded (Property identified) |  |  |  |  | 9814413939
| MoXi Retail Timed Emails - App Fee Not Paid + Docs Uploaded (Property identified) |  |  |  |  | 9814416341
| MoXi Retail Timed Emails - App Fee Not Paid + Docs Missing (TBD) |  |  |  |  | 9814416846
| MoXi Retail Timed Emails - App Fee Not Paid + Docs Uploaded (TBD) |  |  |  |  | 9814417181
| MoXi Retail Timed Emails - App Fee Paid + Docs Missing (TBD) |  |  |  |  | 9814417448
| Synced Contact owner, Phone, Email from SF to AC |  |  |  |  | 9814418350
| Configured 28 emails |  |  |  |  | 9814426359
Attended Salesforce User Management Training (3 sessions) |  | Oscar Gatica | Done |  |  | 9791499866
Bookings Multi-MA Roundrobin Zap + PowerAutomate Setup | Taught Myself Microsoft PowerAutomate to Send Bookings Info to a Onedrive excel sheet,Had Zap pull from the Excel sheet, and coded it to grab all important data points from the customers submission,Had Zap then send that info over to Salesforce | Oscar Gatica | Done | 2025-08-14 | 2025-08-18 | 9804410725
Subitems | Name | Owner | Status | Date | Go Live Date | Item ID (auto generated)
| Taught Myself Microsoft PowerAutomate to Send Bookings Info to a Onedrive excel sheet | Oscar Gatica | Done |  |  | 9851515213
| Had Zap pull from the Excel sheet, and coded it to grab all important data points from the customers submission | Oscar Gatica | Done |  |  | 9851524259
| Had Zap then send that info over to Salesforce | Oscar Gatica | Done |  |  | 9851528904
Created and configured 3 new Booking pages for our BDO's |  | Oscar Gatica | Done | 2025-08-12 | 2025-08-14 | 9819373515
Configure SF Reffinity to send out monthly reports to Approved Partners |  | Oscar Gatica | Stuck |  |  | 9864384613
Re-configure all 18 of the gmail Zaps to start using the Partnerships Inbox |  | Oscar Gatica | Done | 2025-08-19 | 2025-08-21 | 9864392192
Setting up Duplicate Check Rule in SF |  | Oscar Gatica | Done | 2025-08-22 | 2025-08-26 | 9892307582
Review and Revise SF email Opt Out |  | Oscar Gatica | Done |  |  | 9896239818
Enhance B2B AC automation flow |  | Oscar Gatica | Done | 2025-08-27 | 2025-08-29 | 9924129080
Created 2.5month post closing email automation in AC |  | Oscar Gatica | Done | 2025-08-28 | 2025-08-28 | 9930509856
Created Birthday and Anniversary Email flow in SF |  | Oscar Gatica | Done | 2025-08-28 | 2025-08-28 | 9930521696
|  |  |  | 2025-07-28 to 2025-08-28 | 2025-08-11 to 2025-08-29
IT Projects - September
Name | Subitems | Person | Status | Date assigned | Go Live Date | Item ID (auto generated)
General Configurations & Support | Connected Mary's booking page to SF—to create events when clients schedule a discovery session,SF: add a “reasoning” field where the BDO can provide an explanation as to why they are requesting a reassignment on a contact.,Helped Mary with an Encompass issue,Mass updated Mike's B2B contacts into their respective drip campaign,Helped Mary with her Laptop battery problems,Helped Taydra with customer Issues,Helped Carl with SF calling issues,Helped Victoria with o365 application issues,Walked Chris through a couple of Flow Builds,Helped Jason re-configure an outdated Zap | Oscar Gatica | Working on it |  |  | 9956558956
Subitems | Name | Owner | Status | Date | Go Live Date | Item ID (auto generated)
| Connected Mary's booking page to SF—to create events when clients schedule a discovery session | Oscar Gatica | Done | 2025-09-02 | 2025-09-02 | 9956562297
| SF: add a “reasoning” field where the BDO can provide an explanation as to why they are requesting a reassignment on a contact. | Oscar Gatica | Done | 2025-08-29 | 2025-09-04 | 9956958517
| Helped Mary with an Encompass issue | Oscar Gatica | Done | 2025-09-03 | 2025-09-03 | 9966368871
| Mass updated Mike's B2B contacts into their respective drip campaign | Oscar Gatica | Done |  |  | 10043088373
| Helped Mary with her Laptop battery problems | Oscar Gatica | Done |  |  | 10043089202
| Helped Taydra with customer Issues | Oscar Gatica | Done |  |  | 10043089745
| Helped Carl with SF calling issues | Oscar Gatica | Done |  |  | 18054917035
| Helped Victoria with o365 application issues | Oscar Gatica | Done |  |  | 18077974066
| Walked Chris through a couple of Flow Builds |  |  |  |  | 18078037978
| Helped Jason re-configure an outdated Zap |  |  |  |  | 18078082689
Connect Chatgpt to Microsoft 365 tenant |  | Oscar Gatica | Done | 2025-09-03 |  | 9964737479
Re-configured our SMS setup to exclude TX contacts |  | Oscar Gatica | Done | 2025-09-03 | 2025-09-03 | 9966378901
Created Discovery No-Show Email Setup in SF |  | Oscar Gatica | Done | 2025-09-01 | 2025-09-04 | 9968534331
Create Booking Links for BDO's + Guillermo |  | Oscar Gatica | Done | 2025-09-08 | 2025-09-11 | 10001497542
SF Buyer & Seller Agent Emails | Created a flow that creates the buyer business contact and sends them an email,Created a flow that creates the seller business contact and sends them an email | Oscar Gatica | Done | 2025-09-08 | 2025-09-11 | 10033810926
Subitems | Name | Owner | Status | Date | Go Live Date | Item ID (auto generated)
| Created a flow that creates the buyer business contact and sends them an email |  |  |  |  | 10033817419
| Created a flow that creates the seller business contact and sends them an email |  |  |  |  | 10033818529
Created SF Buyer & Seller Agent "Thank You" email from Guillermo |  | Oscar Gatica | Done | 2025-09-10 | 2025-09-12 | 10042959362
Began Discovery Calls with prior Agora Managed Systems, to transition them to us | Migrate Mimecast,Migrate O365,Migrate CodeTwo,Migrate Smarsh,Migrate ActiveDirectory | Oscar Gatica | Working on it | 2025-09-19 |  | 18054914842
Subitems | Name | Owner | Status | Date | Go Live Date | Item ID (auto generated)
| Migrate Mimecast | Oscar Gatica | Working on it |  |  | 18077939075
| Migrate O365 | Oscar Gatica | Working on it |  |  | 18077940142
| Migrate CodeTwo | Oscar Gatica | Working on it |  |  | 18077941083
| Migrate Smarsh | Oscar Gatica | Working on it |  |  | 18077941784
| Migrate ActiveDirectory | Oscar Gatica | Working on it |  |  | 18077945598
Created SF Email Flows based on Stage: "Not Interested, Not Qualified, Future Follow-up" emails |  | Oscar Gatica | Done | 2025-09-17 | 2025-09-19 | 18078051303
Create SF Email Confirmation for Future Follow-Up |  | Oscar Gatica | Done | 2025-09-17 | 2025-09-19 | 18077877509
Created SF flows to send out Emails based on Loan stages |  | Oscar Gatica | Done | 2025-09-23 | 2025-09-25 | 18077858717
Created Drip Campaign & Automation for Pre-Qualified Clients |  | Oscar Gatica | Done | 2025-09-27 | 2025-09-30 | 18077888262
|  |  |  | 2025-09-01 to 2025-09-27 | 2025-09-03 to 2025-09-30
IT Projects - October
Name | Subitems | Person | Status | Date assigned | Go Live Date | Item ID (auto generated)
Enhanced our SF Intro Contact Emails to centralize them into 1 SF flow instead of 6 |  | Oscar Gatica | Done | 2025-10-03 | 2025-10-03 | 18109179770
Created a TBD flow from ENC to SF |  | Oscar Gatica | Done |  |  | 18162254684
Transfered CodeTwo ownership to MoXi |  | Oscar Gatica | Done |  |  | 18246648116
Configured Authenticator Policies in Microsoft EntraID |  | Oscar Gatica | Done |  |  | 18246659023
Migrated all staff members to new authenticator |  | Oscar Gatica | Done |  |  | 18246670986
Exported all Smarsh data |  | Oscar Gatica | Done |  |  | 18246674491
Worked with Agora IT team migrate O365 away from their system |  | Oscar Gatica | Done |  |  | 18246685585
Review SF customer communication [CC and BCC] |  | Oscar Gatica | Working on it |  |  | 18268147485
Configure SMS Notifications in SF for App Fee & Docs Missing | Configured 4 Salesforce Flows,Created 18 SF Text Templates,Conducted a training session to our MA's | Oscar Gatica | Done | 2025-10-28 | 2025-10-31 | 18310948113
Subitems | Name | Owner | Status | Date | Go Live Date | Item ID (auto generated)
| Configured 4 Salesforce Flows | Oscar Gatica | Done |  |  | 18311012466
| Created 18 SF Text Templates | Oscar Gatica | Done |  |  | 18311017071
| Conducted a training session to our MA's | Oscar Gatica | Done |  |  | 18357366966
Onboarded Yatin (AI engineer) |  | Oscar Gatica | Done | 2025-10-29 | 2025-10-29 | 18310970274
Delegate limited access to Agora Team members, to our Accounting Folders |  | Oscar Gatica | Done |  |  | 18311151237
|  |  |  | 2025-10-03 to 2025-10-29 | 2025-10-03 to 2025-10-31
IT Projects - November
Name | Subitems | Person | Status | Date assigned | Go Live Date | Item ID (auto generated)
Quick General Configurations | Helped Taydra Update the Call center,Helped Carl with Salesforce Issue,Helped Troy with Surfshark VPN questions,Answered and walked Mike through a couple of Booking Questions,Corrected duplicate attribute on an old mail account in O365,Helped Chris resolve Customer Loan Issue — wrong site ID,Granted Taydra access to the Underwriting Inbox — per Amy's request,Updated ENC email notification for POA Waiver,Helped Chris resolve SF issue,Helped Taydra resolve customer loan auth issue — customer user error,Updated Cash To Close Est. ENC form, and custom print form to correct fee name | Oscar Gatica | Done |  |  | 18356078842
Subitems | Name | Owner | Status | Date | Go Live Date | Item ID (auto generated)
| Helped Taydra Update the Call center | Oscar Gatica | Done |  |  | 18356081706
| Helped Carl with Salesforce Issue | Oscar Gatica | Done |  |  | 18357122350
| Helped Troy with Surfshark VPN questions | Oscar Gatica | Done |  |  | 18357130953
| Answered and walked Mike through a couple of Booking Questions | Oscar Gatica | Done |  |  | 18357237771
| Corrected duplicate attribute on an old mail account in O365 | Oscar Gatica | Done |  |  | 18357293143
| Helped Chris resolve Customer Loan Issue — wrong site ID | Oscar Gatica | Done |  |  | 18373303154
| Granted Taydra access to the Underwriting Inbox — per Amy's request | Oscar Gatica | Done |  |  | 18373655188
| Updated ENC email notification for POA Waiver | Oscar Gatica | Done | 2025-11-05 | 2025-11-05 | 18376401131
| Helped Chris resolve SF issue | Oscar Gatica | Done |  |  | 18378521541
| Helped Taydra resolve customer loan auth issue — customer user error | Oscar Gatica | Done |  |  | 18378521822
| Updated Cash To Close Est. ENC form, and custom print form to correct fee name | Oscar Gatica | Done |  |  | 18383215009
Migrate users away from ChatGPT and onto Copilot — Pending Decision by AI team |  | Oscar Gatica | Enhancement Request | 2025-11-03 |  | 18357381512
Find solution — email automation to partners, about their loans in process |  | Oscar Gatica | Pending Management Approval |  |  | 18310983953
Review contact that bypassed Double Opt-In |  | Oscar Gatica | Done | 2025-11-03 | 2025-11-04 | 18357513666
Clean up old spam contacts in Kajabi |  | Oscar Gatica | Enhancement Request | 2025-11-04 |  | 18357522485
Created and configured Microsoft Higher Protection Level Policies |  | Oscar Gatica | Done | 2025-11-04 | 2025-11-04 | 18347765858
Build new 54 Week Drip Campaign for Realtor Partners |  | Oscar Gatica | Done |  | 2025-11-04 | 18310975939
Research and Learn to configure Windows Defender Security Policies, to match Mimecast |  | Oscar Gatica | Ongoing Build | 2025-11-03 |  | 18357110928
Gathering Essential ENC forms, to have Turnkey Replicate. Formatting them to best fit in the TurnKey Environment | Created and sent over to Amy for review,Sent the approved required forms to Turnkey. | Oscar Gatica | Working on it | 2025-11-03 |  | 18357172497
Subitems | Name | Owner | Status | Date | Go Live Date | Item ID (auto generated)
| Created and sent over to Amy for review | Oscar Gatica | Done |  |  | 18358688843
| Sent the approved required forms to Turnkey. | Oscar Gatica | Done |  |  | 18360142991
Review Turnkey Borrower Portal — compile list of issues/bugs/updates/missing items |  | Oscar Gatica | Working on it | 2025-11-03 |  | 18357302950
Worked with Jungo to Update MA & BDO Signatures, on profile and on all contacts |  | Oscar Gatica | Done | 2025-11-03 | 2025-11-05 | 18357194581
Working with Jungo to configure and update our Agent Portal |  | Oscar Gatica | Ongoing Build | 2025-10-29 |  | 18357208469
Review contacts with blank Lead Source Origination fields in SF — Fix if an issue exists |  | Oscar Gatica | Done | 2025-11-11 | 2025-11-10 | 18357277451
Helping Justin Securely Log Onto Statebridge’s tenant — Microsoft Issue on their end ¦ made several attempts but connection cannot be established |  | Oscar Gatica | Working on it |  |  | 18357314269
Working on cancelling the SMARSH renewal — Escalated to Management since they are refusing to cancel |  | Oscar Gatica | Done |  | 2025-11-06 | 18357334876
Created new private Sharepoint to store Smarsh Archive |  | Oscar Gatica | Done |  | 2025-11-12 | 18376905972
Sunset Mimecast - Pending Decision ¦ Licenses Expire on Jan |  | Oscar Gatica | Outlining Plan |  | 2025-11-30 | 18357409556
Renew Microsoft Teams, E3, and E5 Licenses — Expire on Nov 22 |  | Oscar Gatica | Working on it |  | 2025-11-22 | 18357551903
Updated MFA to have staff re-authenticate every 12 hours — Enhanced Security |  | Oscar Gatica | Done |  | 2025-11-10 | 18373650689
|  |  |  | 2025-10-29 to 2025-11-11 | 2025-11-04 to 2025-11-30

## active projects-updates
Active Projects | Updates
Item ID | Item Name | Content Type | Content Type | User | Created At | Update Content | Likes Count | Asset IDs | Post ID | Parent Post ID
9547006398 | Restrict Contact Owner, BDO, BDO2 fields in Salesforce & Create Approval Process | Update |  | Oscar Gatica | 08/July/2025 05:55:14 PM | Created an approval process, so that BDO's can submit contact reassignment requests to their Manager. Created a flow that controls which fields get updates based upon the assignment decision. BDOs can no longer assign themselves as Contact Owner, BDO, or BDO2 directly. Instead, they’ll use the Submit for Approval button on the Contact record to request an assignment. Requests will be routed to Guillermo and Jason R. for review. Once approved or denied, the system will handle the assignment automatically and notify the requestor via email. Attached, is a guide for the managers and BDO's. Contact Reassignment Process (BDO).pdf Contact Reassignment Process (Manager).pdf | 0 | 2276391131,2276391132 | 4302154986
9547502351 | Renew Adobe License | Update |  | Oscar Gatica | 08/July/2025 06:07:28 PM | In order to get a discounted price, we closed our old adobe account and opened up a new one. It brought challenges to our users, but we were able to resolve all problems within a couple of days. | 0 |  | 4302174653
9637103869 | B2B Drip Campaign (Zap ¦ ActiveCampaign ¦ Salesforce) | Update |  | Oscar Gatica | 21/July/2025 01:42:23 PM | * Any new developer, broker or re-agent that opts in through our site will be automatically entered into their corresponding drip campaigns. The contact will be assigned to Guillermo to assign out. * Any new contact that is imported or created, will be entered into their respective drip campaign depending on the group they are assigned to. * As for our current business contacts, I bulked batch updated all of them to be entered into their corresponding drip campaign. | 0 |  | 4335149807
9639726544 | Salesforce Milestone Cleanup | Update |  | Oscar Gatica | 21/July/2025 06:37:22 PM | Ran into a mapping issue. So I opted to having Jungo walk me through this integration piece. Side notes: -Deleted Intake (not being used) -Removed Pre-qualification and mapped as Application Under Review | 0 |  | 4336137092
9676179136 | ActiveCampaign 52 week Drip Email Campaign | Update |  | Oscar Gatica | 29/July/2025 03:14:04 PM | Built out the flows, now pending Nick to set up the emails within the flow. | 0 |  | 4358853489
9690146559 | English to Spanish translation solution for Team Meetings. | Update |  | Oscar Gatica | 01/August/2025 05:15:12 PM | Approval was granted. Doing Final testing. | 0 |  | 4370209893
9690146559 | English to Spanish translation solution for Team Meetings. | Update |  | Oscar Gatica | 06/August/2025 05:13:57 PM | Updated the Hello@moxi.global account to have premium, then created a job aid so that LT members can use the premium features. | 0 |  | 4382139424
9710298139 | Updated the Ellie Mae lead source flow from ENC to SF. | Update |  | Oscar Gatica | 30/July/2025 05:10:32 PM | Was caused by an old rule in SF. It is assigned to new contacts created by Encompass that are not in our system. Ex: If an ad brings a lead into SF, that contact will have a record. They then open a loan, the lead source will be whichever ad they came in through. NOT ellie mae. Ex2: If a client goes to our website, clicks on the apply now button, and starts a loan. Since they didn't opt in via an Ad, they will not have a lead source, and will not exist in SF. So when they start a new loan, ENC will create a contact for them, and tag them as Ellie Mae | 0 |  | 4363119859
9710339259 | Configured Voicemail Zap to have quiet hours | Update |  | Oscar Gatica | 30/July/2025 05:17:53 PM | Voicemail Quiet Hours Since our voicemail flow runs through Zapier, and Zapier doesn't natively support time zones, I had to first teach Zapier to convert UTC into PST. Then, I engineered an IF/ELSE flow: >* IF (VM triggers between 8am-5pm PST) -> Send out the voicemail * Else (VM triggers outside of 8am-5pm PST) > * IF (VM trigger is after 5pm PST) -> Wait until 8am next day. * Else (VM trigger is before 8am PST) -> Wait until 8am same day. | 0 |  | 4363133242
9710369017 | Taught myself how to use the Windows PowerShell Command System to run scripts on our Office365 Tenant | Update |  | Oscar Gatica | 30/July/2025 05:25:46 PM | Ran my first script, to make it so that any emails sent in behalf of the anywhere inbox, saves a copy in the Sent Items folder. (Previously was saving on the users personal inbox) | 0 |  | 4363146087
9710372583 | Created a Marketing Touchpoint custom object in SF to capture each time a lead opted in via marketing. | Update |  | Oscar Gatica | 30/July/2025 05:29:01 PM | >* Created a SF Flow, Email Templates, Custom Fields, and Email Alerts to notify the MA when a client re-opts into marketing, and to notify the client that we received their re-opt | 0 |  | 4363151275
9710436935 | Fixed issue with an ENC calculation fields | Update |  | Oscar Gatica | 30/July/2025 05:39:49 PM | >* CX.ACQTAX.OVERRIDE * CX.RECFEE.OVERRIDE | 0 |  | 4363169053
9864384613 | Configure SF Reffinity to send out monthly reports to Approved Partners | Update |  | Oscar Gatica | 25/August/2025 07:18:11 PM | Reffinity can only send reports to one contact at a time—this limits our reporting for larger partner companies. AC is an alternative option, but it isn't built out enough to send out reports with lots of details. | 0 |  | 4431559335
9896239818 | Review and Revise SF email Opt Out | Update |  | Oscar Gatica | 30/September/2025 12:20:25 PM | Chris created an opt out link that can be used in Lightning templates | 0 |  | 4534198365
9964737479 | Connect Chatgpt to Microsoft 365 tenant | Update |  | Oscar Gatica | 30/September/2025 11:58:59 AM | Every user needs to connect their account individually. Let LT know. | 0 |  | 4534097511
9968534331 | Created Discovery No-Show Email Setup in SF | Update |  | Oscar Gatica | 03/September/2025 07:34:14 PM | I created 2 Salesforce flows to meet this need. Details listed below: Flow 1: When a contact's stage is set to "Lead - Discovery Call Scheduled - NO SHOW", a marketing action is created. *The reason why we need the marketing action, is to have emails send out in behalf of the MA. Otherwise, the email will be sent out as the last user who modified the contact or a wide org email like the hello inbox. Flow 2: At the top of the hour, the marketing action activates—checks if the contact has the Do Not Contact box checked. If the contact doesn't, it moves forward. It updates the stage of the contact to "Lead - Discovery Call Scheduled - NO SHOW - Automatic Email Follow-up Sent", then sends the No Show email to the contact in behalf of the MA. Screenshot below: | 0 | 2396235579 | 4458364750
10033810926 | SF Buyer & Seller Agent Emails | Update |  | Oscar Gatica | 11/September/2025 03:20:49 PM | The new Welcome Seller and Welcome Buyer Agent emails are now live. Moving forward, whenever a seller or buyer agent’s email is added to the loan, the system will automatically send them a welcome email in behalf of the MA. There are two ways to enter the contact info: >* Add it in Encompass and let it sync over to Salesforce * Enter it directly in Salesforce Either method will create an individual business contact for each agent and tie it back to the loan and borrower contact. When an email goes out, the MA will be CC’d so that they're always aware. | 0 |  | 4483719787
18077858717 | Created SF flows to send out Emails based on Loan stages | Update |  | Oscar Gatica | 30/September/2025 12:00:21 PM | 2 SF flows were created to send out event emails. 1. Real Deal – Approved – buyer side only: Sends out when the file status is set to "Real Deal - Approved" and the app date is greater than 9/25/25 2. Clear to Close – Lock & Doc (buyer and seller): Sends out when the CTC verified field in ENC is set to yes, then syncs over to SF AND the app date is greater than 9/25/25. | 0 |  | 4534103790
18077877509 | Create SF Email Confirmation for Future Follow-Up | Update |  | Oscar Gatica | 30/September/2025 12:01:47 PM | The Discovery Call Stage Email automations are now live. For any contact with a discovery call scheduled on or after 9/21, the system will automatically send out an email when you update the Stage field. Each Stage (Converted to Realtor, Converted to WHL mortgage Broker, Future Follow-up, Not Interested, Not Qualified, No Further Response from Contact) has its own tailored email that goes out directly from the MA. Important to Note: The email only triggers when the system detects a change in the Stage field. Once you complete a discovery call, update the Stage field to ensure the correct email is sent out. | 0 | 2453635256 | 4534109807
18077888262 | Created Drip Campaign & Automation for Pre-Qualified Clients | Update |  | Oscar Gatica | 30/September/2025 07:50:57 PM | Any new prequalified client that meets these parameters will be entered into the drip campaign moving forward: ICD Approved = Yes And ICD – Loan TBD = Yes And ICD Status = ICD - Credit approved If at any point the loan is moved into the Withdrawal folder, the client will exit the automation. | 0 |  | 4535730556
18310975939 | Build new 54 Week Drip Campaign for Realtor Partners | Update |  | Oscar Gatica | 05/November/2025 12:43:40 PM | Once a contact in SF meets these parameters, they will sync over to AC, which will enter them into a drip campaign. Active Partnership = Yes Agreement Signed = Yes Company Type = Real Estate Brokerage First set of contacts, have been entered in. https://globalmortgage2.lightning.force.com/lightning/r/Report/00OTS000003seA12AI/view?queryScope=userFolders | 0 |  | 4644509764
18310983953 | Find solution — email automation to partners, about their loans in process | Update |  | Oscar Gatica | 05/November/2025 01:01:50 PM | - Reffinity can only send reports to one contact at a time—this limits our reporting for larger partner companies. AC is an alternative option, but it isn't built out enough to send out reports with lots of details. - Another suggestion we have would be to leverage the new Jungo Agent Portal. This portal will give realtors the same information as Reffinity. Realtors would then be able to log into the portal at their own convenience to check for pipeline updates. | 0 |  | 4644916175
18347765858 | Created and configured Microsoft Higher Protection Level Policies | Update |  | Oscar Gatica | 05/November/2025 12:35:27 PM | >* Anti-Phishing:> * Adds user and domain impersonation detection. * Enables mailbox intelligence for sender behavior analysis. * Quarantines high-confidence phishing * Safe Links:> * Adds real-time URL scanning at click-time. * Extends protection to Teams and Office apps. * Rewrites links and blocks malicious redirects. * Safe Attachments:> * Scans attachments in a sandbox before delivery. * Blocks or quarantines detected threats automatically. * Anti-Spam / Anti-Malware:> * Stricter spoof and bulk mail filtering. * Uses enhanced Defender threat intelligence. * Quarantine & Notifications:> * Centralized quarantine for spam, phishing, and malware. * User notifications for quarantined messages. | 0 |  | 4644466857
18357277451 | Review contacts with blank Lead Source Origination fields in SF — Fix if an issue exists | Update |  | Oscar Gatica | 10/November/2025 02:16:41 PM | I reviewed the report and confirmed that the 25-30% of contacts who are missing the LSO fields, were either manually created by a team member, an older contact, or are a re-opt. I went through a couple of contacts from this month’s reporting and noted the reason why the LSO field is blank. See below: To make it easier to identify why a contact doesn’t have an LSO, I added the “Created By” field to the Salesforce report. If a contact was created by anyone other than Chris (since Zapier uses his account for automated contact creation), it means the contact was manually created by an MA and won’t have an LSO unless it’s entered manually. | 0 | 2544873870,2544874217 | 4657643890
18357334876 | Working on cancelling the SMARSH renewal — Escalated to Management since they are refusing to cancel | Update |  | Oscar Gatica | 06/November/2025 06:31:16 PM |  | 0 | 2539027637 | 4649980906